## Test_scenarios
Section | Description | Remarks / Actual outcome | Defect Testing status | Defect development Status
B2B main portal : home page | Linking to B2Bharat with FB, Twitter,Google+, youtube | NA | New | Work in progress
B2B main portal : home page | Sell on B2Bharat : Add Enquiry field in the form | Screenshot | New | Work in progress
B2B main portal : home page | Free member Registration: Remove Payu money redirection for Free member | Screenshot | New | Work in progress
B2B main portal : home page | PayuMoney Cancel navigation : If user cancels the registration after going to payumoney, user must be navigated back to login page. 1.This profile must not be saved if payumoney cancelled. 2.User must be navigated back to Login page. | Screenshot | New | Work in progress
B2B main portal : home page | Registration Option with either payuMoney OR Already paid 1. PayuMoney will work as working 2. If clicked on Already paid, then will user will be navigated to Client portal and user's profile will get saved normally.Profile will be by default de-activate from backend(Admin) as per the existing functionality | NA | New | Work in progress
B2B main portal : Client Catalogue | Client Catalogue : Home Tab -> Certification Achieved (in the bottom) Improvement in look and feel Contact US: Also show email id of client Product page: Unit price with unit | Screenshot | New | Work in progress
B2B Main Portal : Client Mailbox | Issues: Inbox 1. Search Now: Not working 2. Alignment issue 3.Pagination not working 4. Set as flagged not working | Screenshot | New | Work in progress
B2B Main Portal : Search functionality | Issues:search 1. Main search not working with state(EX:Maharashtra)and multiple keywords(EX:paint in pune) 2. Refine search is not working 3. Needs area name in Search result box 4. Company name Hyperlink should navigate to company's catalogue/website. | Screenshot | New | Work in progress
B2B Main Portal : Search functionality | Search alignment improper | Screenshot | Open | Work in progress
Gmail of client: website enquiry | Neelu
Website publish from admin; in company profile; client: Website url OR Catalogue Url(b2bharat.com/gopalPaints) : | Website must only be published through Admin.
B2B Main Portal : Home page --> product list | Unit price with unit: unit price : 160 Litre Selling capacity come with unit | Neelu/santosh
B2B Main Portal : Home page --> 1. Latest Category: open link like in image 2. Whole salers: same 3. Our partners: link should navigate to cateogue /website | Neelu/santosh
B2Bharat: Client catalogue: Product dropdown: based on product name | Click on Product header: show all product page Click on Product from dropdown: single product page
B2bharat--> Send you buy requirement (Side bar) | Back button on Thanks.php : Santosh
B2bharat.com-->client catalogue:Product tab | Send Enquiry form: mandatory remove
Client login: My Profile | Edit my profile: Last name not updating Fax number not updating Website field: non editable (fetch from DB. Only can be fiilled by Admin) Website URL format: www.xyz.com OR www.b2bharat.com/companyName
Client login: Company Profile | Company Detail : 1. Website field: non editable (fetch from DB. Only can be fiilled by Admin) Website URL format: www.xyz.com OR www.b2bharat.com/companyName 2. Social Media: Links not working Buisness Details: Keywords and meta description: not working Category and Image: 1. Remove button on Company Logo; Company image 1; Company image 2 and Company Brochure 2. Company Brochure : must be in PDF also with image format.Also it should be downloadable through catalogue.
Client login: Membership plan | Upgrade not working Renew button missing on Current plan menu
Client Login: Add product | Remove button for image removal Tool bar in manage product (3 places) Tool bar in add product (1 places) Image is not updating in manage product functionality | Santosh
B2Bharat->Enquiry + all form test | 1. If while sending enquiry through feedback form, three tabs of B2bharat are open, then enquries is being send three times. : Bhimashankar 2. Client Product page enquiry: mail going to personal client spam and enquiry@b2bharat.com: and different form for both the email boxes. Vineet/neelu
B2bharat-> company list; Buyer list and seller list (multiple enquiry) | 1.Page crashing while using multiple enquiry 2. Going to client personal email id(spam), enquiry@b2bharat.com and not going to client b2bharat mail box
B2bharat-> catalogue-> contact us page | 1. Enquiry only going to b2bharat mail box, enquiry@b2bharat.com and not going to client personal email. 2. Also need to change format of sent enquiry
B2bharat home page --> Post Buying Leads | Not working with green touch paint and gopal paints

## Sheet1
Testing status | Dev. Status
Open | Work in progress
On hold | Ready for testing
Re-open | On hold
Cancel | Need information
Closed | Rejected
New | Resolved